## Sheet1
| Start Date | Duration
Planning Meeting | 2007-04-09 | 1
Develop Questionnaire | 2007-04-10 | 11
Print and Mail Questionnaire | 2007-04-24 | 9
Receive Responses | 2007-04-27 | 15
Data Entry | 2007-04-27 | 18
Data Analysis | 2007-05-15 | 4
Write Report | 2007-05-21 | 12
Distribute Draft Report | 2007-06-04 | 2
Solicit Comments | 2007-06-05 | 5
Finalize Report | 2007-06-11 | 6
Distribute to Board | 2007-06-18 | 2
Board Meeting | 2007-06-26 | 1